## 00 Read Me
Clarify AI — Enterprise QA Testing Workbook
Application | Clarify AI
Description | AI-powered interview preparation & rehearsal platform with Indian gov-exam MCQ mock tests, live coaching overlay, and dual Stripe/Razorpay billing.
Tech stack | React 18 + TypeScript + Vite + Tailwind/shadcn · Supabase (Auth, Postgres+RLS, Edge/Deno, Storage, Realtime) · Electron · Deepgram · Gemini/OpenAI/Anthropic · Stripe + Razorpay
Portals | Marketing · Auth · Candidate App · Admin · Electron Overlay
Roles | Guest · Free User · Pro User · Max User · Admin
Version under test | 1.0.0 / 1.0.0-beta
Generated | 2026-07-28
HOW TO USE
1 | Open 01 Dashboard — all KPIs and charts are formula-driven. Do not type numbers there.
2 | Maintain Modules (02) and Features (03) as scope changes.
3 | Author/execute cases in 04; link defects in 06 via Bug ID.
4 | Run golden paths in 05 before every RC; fill Daily Log for progress charts.
5 | Execute domain packs 14–16 (Live Coaching, Gov Exam, Billing) — not marketplace.
6 | Complete 19 Production Readiness and 20 Release Sign-Off for Go/No-Go.
7 | All enums use Lists dropdowns. Track Est Hours / Actual Hours on modules, features, cases, E2E, and regression. Use QA Team sheet for roster capacity.
QA TEAM
Kavya Iyer (QA Lead) · Asha Sharma (Senior QA) · Rohan Mehta (QA Engineer) · Priya Nair (QA Engineer) · Dev Patel (SDET)
Green | Pass / Yes
Red | Fail / No / Critical
Yellow | In Progress / Blocked / Medium
Gray | Not Started / Not Run
Blue | Completed / Passed / Ready
SCALING
Designed for hundreds of modules and tens of thousands of test cases. Keep one row per entity; use filters and freeze panes. Dashboard formulas scan to row 5000.
Google Sheets | Upload this .xlsx to Drive → Open with Google Sheets. Charts and data validation transfer; re-check named Lists ranges after import.
SHEET INDEX
01 Dashboard | Live KPIs + charts
02 Module Master | 20 Clarify modules
03 Feature Inventory | Feature coverage matrix
04 Test Case Repository | Executable cases
05 E2E User Flows | Cross-module journeys
06 Bug Tracker | Defect lifecycle
07 UI-UX Testing | Visual / a11y
08 Mobile Responsiveness | Breakpoints
09 API Testing | Edge functions
10 Database Validation | Schema / RLS
11 Authentication Testing | Auth matrix
12 Security Testing | OWASP-style
13 Performance Testing | Latency budgets
14 Live Coaching Testing | Domain: live coach + overlay
15 Gov Exam Mock Testing | Domain: MCQ engine
16 Billing Credits Testing | Domain: Stripe/Razorpay/credits
17 Role Based Testing | Plan + admin RBAC
18 Regression Testing | Release regression pack
19 Production Readiness | Go-live checklist
20 Release Sign-Off | Formal approval
Daily Log | Feeds daily progress chart
Lists | Dropdown vocabulary — do not delete

## 01 Dashboard
Clarify AI — QA Executive Dashboard
Formula-driven · Do not edit KPI cells (protected intent) · Source sheets 02–20 + Daily Log
KEY PERFORMANCE INDICATORS |  | Count |  | Daily Progress |  |  |  | QA Person | Actual Hours
Total Modules | PROGRESS BARS | Passed |  | Date | Executed | Passed | Hours | Kavya Iyer
Total Features | Pass Rate | Failed | [5 empty] | Asha Sharma
Total Test Cases | QA Progress | Blocked | [5 empty] | Rohan Mehta
Passed | Prod Ready | Not Executed | [5 empty] | Priya Nair
Failed | Module Complete | [6 empty] | Dev Patel
Blocked | Hours Burn | Count
Not Executed |  | Critical
In Progress |  | High
Critical Bugs |  | Medium
High Bugs |  | Low
Medium Bugs
Low Bugs |  | Module | Completion %
Overall Pass % |  | Auth & Onboarding
Overall Fail % |  | Dashboard
QA Progress % |  | Live Practice Coach
Production Readiness % |  | Mock Interview
Est Hours (Total) |  | Sessions & Debriefs
Actual Hours (Total) |  | Analytics & Usage
Hours Variance |  | Prep Lab
QA Team Size |  | Documents & Resumes
Answer Bank
Interviews & Calendar
Company Research
Notifications & Profile
Referrals & Guide
Gov Exam Mock Tests
Settings
Admin Portal
Marketing Site
Billing & Credits
Electron Desktop Overlay
Security & Platform

## 02 Module Master
Module Master — Clarify AI (20 core modules)
Module ID | Module Name | Portal | Description | Owner | QA Owner | Priority | Status | Total Features | Completed Features | Pending Features | Est Hours | Actual Hours | Criticality | Dependencies | Remarks
MOD-01 | Auth & Onboarding | Auth Portal | Email/OAuth login, MFA, 5-step onboarding | Auth Lead | Asha Sharma | Critical | In Progress | 8 | 6 | 2 | 20 | 13.2 | Critical | — | Seeded from audit 28 Jul 2026
MOD-02 | Dashboard | Candidate App | Home KPIs, sessions, credits, upcoming interviews | Product | Rohan Mehta | High | Completed | 5 | 5 | 0 | 12.5 | 11 | High | — | Seeded from audit 28 Jul 2026
MOD-03 | Live Practice Coach | Candidate App | Deepgram STT + AI hints/answers + overlay | Live Coach | Priya Nair | Critical | Completed | 10 | 9 | 1 | 25 | 19.8 | Critical | Auth, Billing credits, Deepgram | Seeded from audit 28 Jul 2026
MOD-04 | Mock Interview | Candidate App | Timed mock sessions with AI scoring | Live Coach | Priya Nair | High | In Progress | 7 | 5 | 2 | 17.5 | 11 | High | Sessions, Credits | Seeded from audit 28 Jul 2026
MOD-05 | Sessions & Debriefs | Candidate App | History, detail, AI debrief, scorecard share | Sessions | Priya Nair | High | Completed | 6 | 5 | 1 | 15 | 11 | High | — | Seeded from audit 28 Jul 2026
MOD-06 | Analytics & Usage | Candidate App | Trends, WPM, fillers, credit usage | Analytics | Rohan Mehta | Medium | Completed | 5 | 5 | 0 | 12.5 | 11 | Medium | — | Seeded from audit 28 Jul 2026
MOD-07 | Prep Lab | Candidate App | STAR, rephraser, polish, company Qs | Prep | Asha Sharma | High | Completed | 7 | 7 | 0 | 17.5 | 15.4 | High | — | Seeded from audit 28 Jul 2026
MOD-08 | Documents & Resumes | Candidate App | Upload, parse-resume, gap analysis, OCR | Docs | Priya Nair | High | Completed | 6 | 5 | 1 | 15 | 11 | High | Credits (parse-resume) | Seeded from audit 28 Jul 2026
MOD-09 | Answer Bank | Candidate App | STAR library + AI generate via prep-tool | Prep | Asha Sharma | Medium | In Progress | 4 | 3 | 1 | 10 | 6.6 | Medium | — | Seeded from audit 28 Jul 2026
MOD-10 | Interviews & Calendar | Candidate App | Manual interviews + Google Calendar sync | Scheduling | Rohan Mehta | High | In Progress | 6 | 4 | 2 | 15 | 8.8 | High | — | Seeded from audit 28 Jul 2026
MOD-11 | Company Research | Candidate App | AI company brief + per-user cache | Prep | Asha Sharma | Medium | Completed | 3 | 3 | 0 | 7.5 | 6.6 | Medium | — | Seeded from audit 28 Jul 2026
MOD-12 | Notifications & Profile | Candidate App | Realtime notifications, XP/streak/badges | Growth | Rohan Mehta | Medium | In Progress | 5 | 3 | 2 | 12.5 | 6.6 | Medium | — | Seeded from audit 28 Jul 2026
MOD-13 | Referrals & Guide | Candidate App | Referral credits + in-app guide | Growth | Rohan Mehta | Low | Completed | 3 | 3 | 0 | 7.5 | 6.6 | Low | — | Seeded from audit 28 Jul 2026
MOD-14 | Gov Exam Mock Tests | Candidate App | India gov/competitive MCQ engine | GovExams | Rohan Mehta | Critical | In Progress | 9 | 6 | 3 | 22.5 | 13.2 | Critical | Admin question bank | Seeded from audit 28 Jul 2026
MOD-15 | Settings | Candidate App | Billing, audio, models, security, integrations | Platform | Asha Sharma | High | In Progress | 12 | 8 | 4 | 30 | 17.6 | High | — | Seeded from audit 28 Jul 2026
MOD-16 | Admin Portal | Admin Portal | Users, revenue, questions, flags, support | Admin | Rohan Mehta | Critical | In Progress | 15 | 10 | 5 | 37.5 | 22 | Critical | RLS admin role | Seeded from audit 28 Jul 2026
MOD-17 | Marketing Site | Marketing Portal | Landing, pricing, blog, help, legal | Growth | Kavya Iyer | Medium | Completed | 8 | 8 | 0 | 20 | 17.6 | Medium | — | Seeded from audit 28 Jul 2026
MOD-18 | Billing & Credits | Candidate App | Stripe/Razorpay, packs, ledger, plan gates | Billing | Asha Sharma | Critical | Completed | 10 | 9 | 1 | 25 | 19.8 | Critical | Stripe/Razorpay secrets | Seeded from audit 28 Jul 2026
MOD-19 | Electron Desktop Overlay | Electron Overlay | Always-on-top overlay, hotkeys, window state | Desktop | Dev Patel | Critical | In Progress | 6 | 4 | 2 | 15 | 8.8 | Critical | Live Practice Coach | Seeded from audit 28 Jul 2026
MOD-20 | Security & Platform | All Portals | RLS, webhooks, rate limits, CI, observability | Platform | Dev Patel | Critical | In Progress | 8 | 5 | 3 | 20 | 11 | Critical | — | Seeded from audit 28 Jul 2026
TOTAL

## 03 Feature Inventory
Feature Inventory — coverage matrix
Feature ID | Module | Feature Name | Description | Frontend | Backend | Database | API | Edge Function | Status | Implementation Status | QA Status | Priority | Risk | Owner | QA Owner | Est Hours | Actual Hours | Comments
FEAT-001 | Auth & Onboarding | Email/password login | Login with lockout | Yes | Yes | Yes | Yes | N/A | Completed | Fully Implemented | Passed | Critical | High | Auth Lead | Asha Sharma | 2 | 1.5 | zodResolver
FEAT-002 | Auth & Onboarding | OAuth providers | Google/GitHub OAuth | Yes | Yes | Yes | Yes | N/A | Completed | Fully Implemented | In Testing | Critical | Medium | Auth Lead | Asha Sharma | 3 | 2
FEAT-003 | Auth & Onboarding | TOTP MFA | Settings security MFA | Yes | Yes | Yes | Yes | N/A | In Progress | Fully Implemented | Not Tested | High | High | Auth Lead | Asha Sharma | 4 | 0
FEAT-004 | Live Practice Coach | Deepgram streaming STT | Mic + system audio | Yes | Yes | Yes | Yes | Yes | Completed | Fully Implemented | Passed | Critical | Critical | Live Coach | Priya Nair | 6 | 5.5 | deepgram-token
FEAT-005 | Live Practice Coach | AI answer generation | generate-answer + credits | Yes | Yes | Yes | Yes | Yes | Completed | Fully Implemented | In Testing | Critical | Critical | Live Coach | Priya Nair | 5 | 3 | Overlay requires Pro
FEAT-006 | Live Practice Coach | Desktop overlay hotkeys | Central hotkey registry | Yes | N/A | N/A | N/A | N/A | Completed | Fully Implemented | Passed | High | Medium | Desktop | Dev Patel | 2 | 1.5 | P1-6
FEAT-007 | Billing & Credits | Stripe checkout Pro/Max | create-checkout price IDs | Yes | Yes | Yes | Yes | Yes | Completed | Fully Implemented | In Testing | Critical | Critical | Billing | Asha Sharma | 5 | 4 | Enterprise IDs wired
FEAT-008 | Billing & Credits | Razorpay INR order | One-time order + webhook | Yes | Yes | Yes | Yes | Yes | In Progress | Partial | Failed | Critical | High | Billing | Asha Sharma | 4 | 3.5 | No recurring
FEAT-009 | Billing & Credits | Credit ledger deduct | deductCreditsAtomic | Partial | Yes | Yes | Yes | Yes | Completed | Fully Implemented | Passed | Critical | Critical | Billing | Dev Patel | 3 | 2.5
FEAT-010 | Documents & Resumes | Onboarding free parse | First parse free once | Yes | Yes | Yes | Yes | Yes | Completed | Fully Implemented | Passed | High | High | Docs | Priya Nair | 3 | 2 | x-clarify-onboarding-parse
FEAT-011 | Documents & Resumes | Gap analysis charge | gap_analysis = 10 credits | Yes | Yes | Yes | Yes | Yes | Completed | Fully Implemented | In Testing | High | Medium | Docs | Priya Nair | 2.5 | 1
FEAT-012 | Gov Exam Mock Tests | Atomic create/submit | create-test / submit-test | Yes | Yes | Yes | Yes | Yes | Completed | Fully Implemented | Passed | Critical | High | GovExams | Rohan Mehta | 5 | 4.5 | Thin bank
FEAT-013 | Gov Exam Mock Tests | Admin exam filter | Display string map | Yes | Yes | Yes | N/A | Partial | Completed | Fully Implemented | Passed | High | Medium | Admin | Rohan Mehta | 2 | 1.5 | P1-5
FEAT-014 | Admin Portal | Revenue USD/INR | Subscriptions + paise | Yes | Yes | Yes | N/A | N/A | Completed | Fully Implemented | Passed | Critical | High | Admin | Rohan Mehta | 4 | 3 | P0-6
FEAT-015 | Answer Bank | Generate with AI | prep-tool star_method | Yes | Yes | Yes | Yes | Yes | Completed | Fully Implemented | In Testing | Medium | Low | Prep | Asha Sharma | 3 | 1.5 | P3 wire
FEAT-016 | Interviews & Calendar | Google Calendar sync | sync-calendar Pro gate | Yes | Yes | Yes | Yes | Yes | Blocked | Partial | Blocked | High | Medium | Scheduling | Rohan Mehta | 4 | 1 | 501 w/o secrets
FEAT-017 | Sessions & Debriefs | Null score display | Not scored vs 0 | Yes | N/A | Yes | N/A | N/A | Completed | Fully Implemented | Passed | Medium | Low | Sessions | Priya Nair | 1.5 | 1 | P1-7
FEAT-018 | Marketing Site | Pricing Max $79 | enterprise monthlyPrice | Yes | N/A | N/A | N/A | N/A | Completed | Fully Implemented | Passed | High | Low | Growth | Kavya Iyer | 1 | 0.5 | P2-4
FEAT-019 | Electron Desktop Overlay | Window min size | 360×320 clamp | Yes | N/A | N/A | N/A | N/A | Completed | Fully Implemented | Passed | Medium | Low | Desktop | Dev Patel | 1.5 | 1 | P1-9
FEAT-020 | Security & Platform | Refund clawback | charge.refunded safe | N/A | Yes | Yes | Yes | Yes | In Progress | Fully Implemented | In Testing | Critical | High | Platform | Dev Patel | 4 | 2 | P4-2
TOTAL

## 04 Test Case Repository
Test Case Repository — Clarify AI
Test Case ID | Requirement ID | Module | Sub Module | Feature | Screen | User Role | Priority | Severity | Test Scenario | Test Case | Preconditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Status | Bug ID | Tester | Est Hours | Actual Hours | Execution Date | Build Version | Environment | Browser | Device | Platform | Automation | Regression | Smoke | Sanity | Sprint | Release | Remarks
TC-001 | REQ-AUTH-01 | Auth & Onboarding | Login | Email login | /login | Free User | Critical | Critical | Valid credentials | User signs in with email/password | Verified account | 1. Open /login 2. Enter credentials 3. Submit | Redirect to /app or onboarding | Landed on dashboard | Pass | Completed |  | Asha Sharma | 1 | 0.75 | 2026-07-28 | 1.0.0 | Staging | Chrome | Desktop | Web | Manual | Yes | Yes | Yes | Sprint 26 | 1.0.0-beta
TC-002 | REQ-AUTH-02 | Auth & Onboarding | Login | Lockout | /login | Free User | High | High | Repeated failures | Lockout after threshold | Test account | 1. Fail login repeatedly 2. Observe message | Temporary lockout shown |  | Not Run | Ready |  | Asha Sharma | 1.5 | 0 |  | 1.0.0 | Staging | Chrome | Desktop | Web | Manual | Yes | No | Yes | Sprint 26 | 1.0.0-beta
TC-003 | REQ-LIVE-01 | Live Practice Coach | STT | Deepgram stream | /app/live | Pro User | Critical | Critical | Mic open | Near-real-time transcript | Pro + mic permission | 1. Start live 2. Speak 3. Observe transcript | Segments appear under 2s | OK | Pass | Completed |  | Priya Nair | 2 | 1.5 | 2026-07-28 | 1.0.0 | Staging | Electron | Laptop | Windows | Manual | Yes | Yes | No | Sprint 26 | 1.0.0-beta
TC-004 | REQ-LIVE-02 | Live Practice Coach | Overlay | Pro gate | /app/live/overlay | Free User | Critical | High | Free overlay blocked | Server rejects overlay capture | Free account | 1. Attempt overlay capture 2. Check response | 403 / upgrade required | 403 returned | Pass | Completed | BUG-001 | Dev Patel | 1.5 | 1.25 | 2026-07-28 | 1.0.0 | Staging | Electron | Desktop | Windows | Candidate | Yes | Yes | No | Sprint 26 | 1.0.0-beta | Retest after P0-3
TC-005 | REQ-BILL-01 | Billing & Credits | Checkout | Max Stripe price | /pricing | Free User | Critical | Critical | Upgrade Max | Enterprise price id used | Stripe test keys | 1. Select Max 2. Checkout 3. Inspect price | Non-empty enterprise price | OK | Pass | Completed |  | Asha Sharma | 2 | 1.5 | 2026-07-28 | 1.0.0 | Staging | Chrome | Desktop | Web | Manual | Yes | Yes | Yes | Sprint 26 | 1.0.0-beta | P0-1
TC-006 | REQ-BILL-02 | Billing & Credits | Webhook | payment_failed | stripe-webhook | Pro User | Critical | Critical | Failed invoice | Wallet not wiped | credits=500 | 1. Simulate invoice.payment_failed 2. Read credits | Credits remain 500 | Unchanged | Pass | Completed |  | Dev Patel | 1.5 | 1 | 2026-07-28 | 1.0.0 | CI | N/A | Desktop | Web | Automated | Yes | Yes | No | Sprint 26 | 1.0.0-beta | P0-2
TC-007 | REQ-DOC-01 | Documents & Resumes | Parse | Free onboarding parse | /onboarding | Free User | High | Medium | First parse free | No deduct on first onboarding parse | onboarding_completed=false | 1. Upload resume 2. Check ledger | Free path / no deduct |  | Not Run | Ready |  | Priya Nair | 1.5 | 0 |  | 1.0.0 | Staging | Chrome | Desktop | Web | Manual | Yes | No | Yes | Sprint 26 | 1.0.0-beta
TC-008 | REQ-GOV-01 | Gov Exam Mock Tests | Submit | Atomic submit | /app/mock-test/session/:id | Free User | Critical | High | Submit answers | Score persisted once | Active test | 1. Answer 2. Submit 3. Open results | Score + breakdown | OK | Pass | Completed |  | Rohan Mehta | 2 | 1.75 | 2026-07-28 | 1.0.0 | Staging | Chrome | Android Phone | Android | Manual | Yes | Yes | Yes | Sprint 26 | 1.0.0-beta
TC-009 | REQ-ADM-01 | Admin Portal | Revenue | USD vs INR | /app/admin/revenue | Admin | Critical | High | Admin revenue view | Currencies separate | Admin + sample data | 1. Open Revenue 2. Compare hand calc | USD MRR + INR separate | OK | Pass | Completed |  | Kavya Iyer | 2.5 | 2 | 2026-07-28 | 1.0.0 | Staging | Chrome | Desktop | Web | Manual | Yes | No | No | Sprint 26 | 1.0.0-beta | P0-6
TC-010 | REQ-APP-01 | Dashboard | Routing | In-app 404 | /app/does-not-exist | Pro User | Medium | Low | Unknown route | NotFound in AppShell | Authenticated | 1. Navigate unknown /app path | In-app NotFound | OK | Pass | Completed |  | Asha Sharma | 0.5 | 0.25 | 2026-07-28 | 1.0.0 | Staging | Chrome | Desktop | Web | Manual | Yes | Yes | Yes | Sprint 26 | 1.0.0-beta | P1-4
TC-011 | REQ-LIVE-03 | Live Practice Coach | Credits | Hint deduct | /app/live | Pro User | High | High | Insufficient credits | 402 when wallet low | credits below cost | 1. Drain credits 2. Request hint | 402 + message | In progress | In Progress | In Progress |  | Dev Patel | 1.5 | 0.5 | 2026-07-28 | 1.0.0 | Staging | Chrome | Desktop | Web | Candidate | Yes | No | No | Sprint 26 | 1.0.0-beta
TC-012 | REQ-SEC-01 | Security & Platform | Authz | Non-admin admin route | /app/admin | Free User | Critical | Critical | Unauthorized admin | Redirect / deny | Non-admin user | 1. Open /app/admin | Denied | Denied | Pass | Completed |  | Kavya Iyer | 1 | 0.75 | 2026-07-28 | 1.0.0 | Staging | Chrome | Desktop | Web | Manual | Yes | Yes | Yes | Sprint 26 | 1.0.0-beta
TOTAL

## 05 E2E User Flows
End-to-End User Flows — golden paths
Flow ID | Flow Name | Portal | Start Page | End Page | Steps | Expected Outcome | Actual Outcome | Pass | Risk | Dependencies | QA Owner | Est Hours | Actual Hours | Comments
E2E-01 | Signup to Onboarding to Dashboard | Auth Portal | /signup | /app/dashboard | 1. Sign up 2. Verify email 3. Complete 5 steps 4. Land dashboard | Profile + onboarding_completed + starter credits | OK on Staging | Pass | High | Auth, Email | Asha Sharma | 3 | 2.5
E2E-02 | Free to Pro Stripe checkout | Candidate App | /pricing | /app/settings/billing | 1. Choose Pro 2. Stripe Checkout 3. Webhook 4. Open Billing | plan=pro, credits granted, ledger entry |  | Not Run | Critical | Stripe test keys | Asha Sharma | 4 | 0 | Money path
E2E-03 | Live coach rehearsal | Candidate App | /app/live | /app/sessions/:id | 1. Start 2. Audio 3. Generate answer 4. End 5. Debrief | Session + transcript + debrief | OK | Pass | Critical | Deepgram, Gemini, Credits | Priya Nair | 5 | 4
E2E-04 | Gov exam create to results | Candidate App | /app/mock-test | /app/mock-test/results/:id | 1. Select exam 2. create-test 3. Answer 4. submit 5. Results | Atomic score, no double submit | OK | Pass | High | Question bank | Rohan Mehta | 3.5 | 3 | Thin content
E2E-05 | Admin seed to candidate test | Admin Portal | /app/admin/seed-questions | /app/mock-test | 1. Import questions 2. Candidate creates test | Imported questions available | Blocked | Blocked | High | Admin, Gemini PDF | Rohan Mehta | 4 | 1
E2E-06 | Electron overlay boot | Electron Overlay | Clarify AI.exe | Overlay window | 1. Launch 2. Auth if needed 3. Overlay topmost 4. Hotkey | Overlay-only shell |  | Not Run | Critical | Code signing deferred | Dev Patel | 3 | 0 | Unsigned beta OK
TOTAL

## 06 Bug Tracker
Bug Tracker
Bug ID | Title | Description | Module | Feature | Environment | Browser | Device | OS | Severity | Priority | Status | Assigned To | Reported By | Found Date | Fixed Date | Retest Date | Build | Sprint | Root Cause | Resolution | Screenshot Link | Video Link | Comments
BUG-001 | Free user overlay capture allowed | Overlay path succeeded for free before Pro gate | Live Practice Coach | Pro gate overlay | Staging | Electron | Desktop | Windows | High | Critical | Closed | Live Coach | Dev Patel | 2026-07-23 | 2026-07-27 | 2026-07-28 | 1.0.0 | Sprint 26 | Logic Bug | requirePlan pro on overlay |  |  | Retested TC-004
BUG-002 | Razorpay plan does not auto-renew | pro_monthly is one-time Order only | Billing & Credits | Razorpay INR | Production | Chrome | Desktop | Windows | High | High | Open | Billing | Asha Sharma | 2026-07-18 |  |  | 1.0.0 | Sprint 25 | Design Gap |  |  |  | Roadmap — CHANGELOG
BUG-003 | Google Calendar sync 501 | Missing OAuth secrets in staging | Interviews & Calendar | Google Calendar sync | Staging | Chrome | Laptop | macOS | Medium | High | Blocked | Scheduling | Priya Nair | 2026-07-25 |  |  | 1.0.0 | Sprint 26 | Config/Env |  |  |  | Need secrets
BUG-004 | Gov exam bank too thin | ~26 seeded MCQs only | Gov Exam Mock Tests | Question bank | Staging | Chrome | Desktop | Windows | Medium | High | Open | GovExams | Kavya Iyer | 2026-07-14 |  |  | 1.0.0 | Sprint 24 | Design Gap |  |  |  | Content gap
BUG-005 | Unsigned Windows installer | SmartScreen warn; signAndEditExecutable false | Electron Desktop Overlay | Code signing | Production | N/A | Desktop | Windows | Low | Medium | Won't Fix | Desktop | Dev Patel | 2026-07-08 |  |  | 1.0.0 | Sprint 24 | Config/Env | Deferred pending cert |  |  | P4-6
BUG-006 | Admin table overflow on mobile | Users table hard to use under 768px | Admin Portal | Admin users | Staging | Chrome | Android Phone | Android | Low | Low | Open | Admin | Rohan Mehta | 2026-07-26 |  |  | 1.0.0 | Sprint 26 | UI Regression |  | https://example.com/shot.png

## 07 UI-UX Testing
UI/UX Testing
Screen | Component | Alignment | Spacing | Responsive | Typography | Icons | Accessibility | Dark Mode | Light Mode | Animation | Pass | Remarks
/pricing | Plan cards | Pass | Pass | Pass | Pass | Pass | Partial | Pass | Pass | Pass | Pass | Max $79
/app/live | Transcript panel | Pass | Pass | Partial | Pass | Pass | Partial | Pass | Pass | Pass | Pass | Electron primary
/app/dashboard | KPI cards | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass
/app/admin/revenue | USD/INR charts | Pass | Pass | Pass | Pass | Pass | Partial | Pass | Pass | N/A | Pass
/login | Auth form | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | N/A | Pass

## 08 Mobile Responsiveness
Mobile Responsiveness
Screen | Android | iPhone | Tablet | Landscape | Portrait | Small Screen | Medium Screen | Large Screen | Responsive | Pass | Comments
/app/dashboard | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Yes | Pass | MobileNav partial
/app/mock-test/session | Pass | Pass | Pass | Partial | Pass | Pass | Pass | Pass | Yes | Pass
/pricing | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Yes | Pass
/app/live | Fail | Fail | Partial | N/A | N/A | Fail | Partial | Pass | Partial | Fail | Desktop-first
/app/admin/users | Partial | Partial | Pass | Pass | Pass | Partial | Pass | Pass | Partial | Partial | Wide tables

## 09 API Testing
API Testing — Supabase Edge Functions
API Name | Method | Endpoint | Authentication | Headers | Request | Expected Response | Actual Response | Status Code | Performance | Security | Pass | Comments
Create Checkout | POST | /functions/v1/create-checkout | Bearer JWT | Authorization, apikey | {"plan":"enterprise"} | Checkout URL | URL ok | 200 | Good | Pass | Pass | Enterprise price
Parse Resume | POST | /functions/v1/parse-resume | Bearer JWT | x-clarify-onboarding-parse | multipart | Parsed JSON | OK | 200 | Acceptable | Pass | Pass | Free once
Generate Answer | POST | /functions/v1/generate-answer | Bearer JWT | Authorization | {"mode":"overlay"} | 403 free overlay | 403 | 403 | Excellent | Pass | Pass | Pro gate
Razorpay Order | POST | /functions/v1/razorpay-create-order | Bearer JWT | Authorization | {"pack":"credits_50"} | order_id | OK | 200 | Good | Pass | Pass | Rate limited
Stripe Webhook | POST | /functions/v1/stripe-webhook | Webhook HMAC | Stripe-Signature | invoice.payment_failed | 200 credits intact | 200 | 200 | Excellent | Pass | Pass | P0-2
Sync Calendar | POST | /functions/v1/sync-calendar | Bearer JWT | Authorization | {} | 501 or events | 501 | 501 | N/A | Pass | Blocked | Secrets

## 10 Database Validation
Database Validation
Table | Columns | Constraints | Relationships | Insert | Update | Delete | Foreign Keys | Indexes | Triggers | Views | Validation Status | Remarks
profiles | id, credits, plan, onboarding_completed, streak_days | PK=auth.users | 1:1 auth.users | Pass | Pass | Pass | Pass | Pass | Partial | N/A | Pass
subscriptions | user_id, plan, status, stripe ids | status checks | profiles | Pass | Pass | Pass | Pass | Pass | N/A | N/A | Pass | MRR source
credit_transactions | user_id, amount, reason | signed amount | profiles | Pass | N/A | N/A | Pass | Pass | N/A | N/A | Pass | Not money
payment_orders | amount_paise, status | incl refunded | profiles | Pass | Pass | N/A | Pass | Pass | N/A | N/A | Pass | INR
sessions | nullable scores | RLS user-owned | answers/debriefs | Pass | Pass | Pass | Pass | Pass | N/A | N/A | Pass | Null≠0
questions / mock_tests | exam_type, options jsonb | RLS | exam bank | Pass | Pass | Pass | Pass | Partial | N/A | N/A | Partial | Thin seed

## 11 Authentication Testing
Authentication Testing
Portal/Role | Login | Signup | Forgot Password | Reset Password | OTP | Email Verification | MFA | Role Permissions | Session | Logout | Unauthorized Access | Status | Remarks
Guest | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Pass | Pass | Public marketing
Free User | Pass | Pass | Pass | Pass | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Limited live
Pro User | Pass | Pass | Pass | Pass | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Overlay+calendar
Max User | Pass | Pass | Pass | Pass | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Priority models
Admin | Pass | N/A | Pass | Pass | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Pass | requireAdmin

## 12 Security Testing
Security Testing (OWASP-style)
Target | SQL Injection | XSS | CSRF | Rate Limiting | Authentication | Authorization | File Upload | Input Validation | Sensitive Data | Headers | Cookies | JWT | Encryption | Status | Remarks
Edge shared utils | Pass | Pass | Pass | Pass | Pass | Pass | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Pass | BYOK removed
parse-document | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Pass | N/A | Pass | Pass | Pass | Key in header
stripe-webhook | N/A | N/A | Pass | N/A | Pass | Pass | N/A | Pass | Pass | Pass | N/A | N/A | Pass | Pass | HMAC
Admin bulk_update_users | Pass | N/A | Pass | N/A | Pass | Pass | N/A | Pass | Pass | N/A | N/A | Pass | Pass | Pass | M5
Resume storage | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Bucket RLS
.env.production history | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Fail | N/A | N/A | Partial | N/A | Fail | Rotate anon key

## 13 Performance Testing
Performance Testing
Screen | API | Load Time | TTFB | Database Query | Memory | CPU | Network | Optimization Needed | Status
/app/dashboard | profile+sessions | 1200ms | 180ms | 90ms | 85MB | 12% | 220KB | No | Pass
/app/live | generate-answer | 900ms | 200ms | 40ms | 140MB | 28% | 80KB | Partial | Pass
/app/admin/users | paginated users | 2100ms | 320ms | 400ms | 110MB | 18% | 450KB | Yes | Partial
/pricing | billing_settings | 800ms | 150ms | 50ms | 70MB | 8% | 160KB | No | Pass
/app/mock-test/session | select-test-questions | 1500ms | 250ms | 180ms | 95MB | 15% | 300KB | Partial | Pass

## 14 Live Coaching Testing
Domain: Live Coaching & Electron Overlay (replaces Marketplace)
Case ID | STT Stream | Diarization | AI Hint | AI Answer | Credit Deduct | Overlay Window | Hotkeys | Pro Gate | Session Persist | Debrief Link | Electron Boot | Pass | Status | Comments
LC-01 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Completed | Pro happy path
LC-02 | Pass | Pass | Pass | N/A | Pass | N/A | N/A | N/A | Pass | Pass | N/A | Pass | Completed | Web live
LC-03 | Pass | Partial | Fail | Fail | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Fail | In Progress | 402 path TC-011
LC-04 | N/A | N/A | N/A | N/A | N/A | Not Run | Pass | Pass | N/A | N/A | Not Run | Not Run | Ready | Packaged unsigned
LC-05 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Partial | Pass | Completed | Hotkey no dup

## 15 Gov Exam Mock Testing
Domain: Gov Exam Mock Test Engine (replaces Checkout)
Case ID | Exam Select | Create Test | Question Load | Timer | Answer Save | Submit Atomic | Score Persist | Results UI | Analytics | Admin Filter | PDF Import | Bank Coverage | Pass | Status | Comments
GE-01 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | N/A | N/A | Partial | Pass | Completed | Happy path
GE-02 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Partial | N/A | N/A | Partial | Pass | Completed | Idempotent submit
GE-03 | Pass | Pass | Partial | Pass | Pass | Pass | Pass | Pass | Pass | N/A | N/A | Fail | Partial | In Progress | Thin bank
GE-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Pass | Completed | P1-5 filter
GE-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Blocked | N/A | Blocked | Blocked | Provider quota

## 16 Billing Credits Testing
Domain: Billing, Credits & Subscriptions (replaces Payment)
Case ID | Gateway | Success | Failure | Cancel | Timeout | Webhook | Refund | Partial Refund | Duplicate Payment | Credit Grant | Credit Clawback | Plan Gate | Transaction History | Settlement | Pass | Status | Comments
BL-01 | Stripe | Pass | Pass | Pass | Not Run | Pass | Not Run | Not Run | Pass | Pass | N/A | Pass | Pass | N/A | Pass | Completed | Pro monthly
BL-02 | Stripe | Pass | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Pass | N/A | Pass | Pass | N/A | Pass | Completed | Max price IDs
BL-03 | Stripe | N/A | Pass | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Pass | Completed | payment_failed wallet
BL-04 | Razorpay | Pass | Pass | Pass | Not Run | Pass | Not Run | N/A | Pass | Pass | N/A | Partial | Pass | N/A | Pass | Completed | One-time only
BL-05 | Stripe | N/A | N/A | N/A | N/A | Pass | Not Run | Not Run | N/A | N/A | Not Run | N/A | Pass | N/A | Not Run | Ready | P4-2 refund
BL-06 | Both | Pass | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Pass | N/A | Pass | Pass | N/A | Pass | Completed | Settings ledger

## 17 Role Based Testing
Role Based Testing — Clarify plan entitlements
Permission/Feature | Module | Guest | Free User | Pro User | Max User | Admin | Permissions | Status | Expected Summary
Access /app | Auth & Onboarding | No | Yes | Yes | Yes | Yes | Auth required | Pass | Guests → login
Live answer limited | Live Practice Coach | No | Yes | Yes | Yes | Yes | Free limited | Pass | live_rehearsal
Desktop overlay | Live Practice Coach | No | No | Yes | Yes | Yes | Pro+ | Pass | requirePlan pro
Company research | Company Research | No | No | Yes | Yes | Yes | Pro+ | Pass
Calendar sync | Interviews & Calendar | No | No | Yes | Yes | Yes | Pro+ | Pass
Priority models | Billing & Credits | No | No | No | Yes | Yes | Max | Pass
Admin revenue | Admin Portal | No | No | No | No | Yes | admin role | Pass | requireAdmin
Promo CRUD | Admin Portal | No | No | No | No | Yes | admin | Pass
View pricing | Marketing Site | Yes | Yes | Yes | Yes | Yes | Public | Pass

## 18 Regression Testing
Regression Testing
Regression ID | Module | Feature | QA Owner | Executed | Pass | Fail | Blocked | Est Hours | Actual Hours | Remarks
REG-01 | Auth & Onboarding | Login/OAuth/MFA | Asha Sharma | Yes | 4 | 0 | 0 | 4 | 3.5 | Smoke green
REG-02 | Live Practice Coach | STT + answer + overlay | Priya Nair | Yes | 4 | 0 | 0 | 6 | 5 | BUG-001 closed
REG-03 | Billing & Credits | Checkout + webhooks | Asha Sharma | Yes | 5 | 0 | 0 | 5 | 4.5 | Money path
REG-04 | Gov Exam Mock Tests | Create/submit/results | Rohan Mehta | Yes | 3 | 0 | 1 | 4 | 3 | PDF blocked
REG-05 | Admin Portal | Users/revenue/questions | Rohan Mehta | Yes | 4 | 0 | 0 | 4 | 3.5
REG-06 | Electron Desktop Overlay | Boot + hotkeys | Dev Patel | Partial | 2 | 0 | 1 | 3 | 1.5 | Unsigned
TOTAL

## 19 Production Readiness
Production Readiness Checklist
Module | Feature Complete | API Complete | Database Ready | Security Passed | Performance Passed | Responsive | Accessibility | SEO | Monitoring | Logging | Deployment Ready | Backup | Recovery | Documentation | Ready Count | Total | Readiness % | Status | Remarks
Auth & Onboarding | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Partial | Yes | Yes | Yes | Yes | Yes | Yes |  | 14
Live Practice Coach | Yes | Yes | Yes | Yes | Yes | Partial | Partial | N/A | Yes | Yes | Yes | Yes | Partial | Yes |  | 14
Billing & Credits | Yes | Yes | Yes | Yes | Yes | Yes | Partial | N/A | Partial | Yes | Yes | Yes | Partial | Yes |  | 14
Gov Exam Mock Tests | Partial | Yes | Partial | Yes | Yes | Yes | Partial | Partial | Partial | Yes | Partial | Yes | Partial | Partial |  | 14
Admin Portal | Partial | Yes | Yes | Yes | Partial | Partial | Partial | N/A | Partial | Yes | Yes | Yes | Partial | Partial |  | 14
Electron Desktop Overlay | Partial | N/A | N/A | Partial | Yes | N/A | Partial | N/A | Partial | Partial | Partial | Yes | Partial | Partial |  | 14
Marketing Site | Yes | N/A | Yes | Yes | Yes | Yes | Partial | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  | 14
Security & Platform | Partial | Yes | Partial | Partial | Yes | N/A | N/A | N/A | Partial | Yes | Yes | Yes | Partial | Yes |  | 14

## 20 Release Sign-Off
Release Sign-Off
Release Version | Build | Environment | QA Lead | Developer Lead | Product Owner | Passed | Known Issues | Blockers | Risk Level | Deployment Approval | Go/No-Go | Remarks
1.0.0-beta | 1.0.0 | Staging | Kavya Iyer | Dev Lead | Product | Yes | BUG-002 no Razorpay renew; BUG-004 thin bank; unsigned Electron | Calendar 501 without secrets | Medium | Pending | Conditional Go | Closed beta OK; hold full prod
1.0.0 | 1.0.0 | Production | Kavya Iyer | Dev Lead | Product | No | See CHANGELOG deferred | Code signing; anon key rotation | High | Pending | No-Go | Await cert + content seed
1.0.1 | TBD | Staging | Kavya Iyer | Dev Lead | Product | No |  |  | Low | Deferred | No-Go | Placeholder

## QA Team
QA Team Roster — Clarify AI
QA Person | Role | Email | Capacity Hrs/Week | Skills Focus | Assigned Cases | Est Hours Assigned | Actual Hours Logged | Utilization % | Status | Remarks
Kavya Iyer | QA Lead | kavya.iyer@clarify.ai | 40 | Sign-off, regression, UAT |  |  |  |  | Active
Asha Sharma | Senior QA | asha.sharma@clarify.ai | 40 | Billing, auth, API |  |  |  |  | Active
Rohan Mehta | QA Engineer | rohan.mehta@clarify.ai | 40 | Gov exams, mobile, admin |  |  |  |  | Active
Priya Nair | QA Engineer | priya.nair@clarify.ai | 40 | Live coach, documents, E2E |  |  |  |  | Active
Dev Patel | SDET | dev.patel@clarify.ai | 40 | Automation, webhooks, Electron |  |  |  |  | Active
TOTAL

## Daily Log
Daily Progress Log (feeds Dashboard chart)
Date | QA Person | Cases Executed | Passed | Failed | Blocked | Bugs Opened | Bugs Closed | Hours Logged | Remarks
2026-07-22 | Asha Sharma | 8 | 6 | 1 | 0 | 1 | 0 | 4.5 | Sprint 26 execution
2026-07-23 | Priya Nair | 10 | 7 | 0 | 0 | 0 | 0 | 5 | Sprint 26 execution
2026-07-24 | Rohan Mehta | 12 | 8 | 0 | 0 | 1 | 0 | 5.5 | Sprint 26 execution
2026-07-25 | Dev Patel | 14 | 9 | 1 | 0 | 0 | 0 | 6 | Sprint 26 execution
2026-07-26 | Kavya Iyer | 16 | 10 | 0 | 1 | 1 | 1 | 6.5 | Sprint 26 execution
2026-07-27 | Asha Sharma | 18 | 11 | 0 | 0 | 0 | 1 | 7 | Sprint 26 execution
2026-07-28 | Priya Nair | 20 | 12 | 1 | 0 | 1 | 1 | 7.5 | Sprint 26 execution
TOTAL

## Lists
Status | PassFail | Priority | Severity | Environment | Browser | Device | Platform | YesNo | QAStatus | BugStatus | Risk | Criticality | Automation | SecurityResult | ReadyStatus | Decision | Approval | PerfRating | HttpMethod | StatusCode | AuthType | Sprint | Release | RootCause | Modules | Portals | Roles | Testers | Owners | ImplStatus | Coverage | ModuleStatus
Not Started | Pass | Critical | Critical | Local | Chrome | Desktop | Web | Yes | Not Tested | New | Critical | Critical | Manual | Pass | Ready | Go | Approved | Excellent | GET | 200 | None | Sprint 24 | 1.0.0-beta | Logic Bug | Auth & Onboarding | Marketing Portal | Guest | Kavya Iyer | Auth Lead | Fully Implemented | Yes | Not Started
In Progress | Fail | High | High | Staging | Edge | Laptop | Windows | No | In Testing | Open | High | High | Automated | Fail | Not Ready | No-Go | Pending | Good | POST | 201 | Bearer JWT | Sprint 25 | 1.0.0 | Missing Validation | Dashboard | Auth Portal | Free User | Asha Sharma | Product | Partial | No | In Progress
Completed | Blocked | Medium | Medium | Production | Firefox | iPhone | macOS | Partial | Passed | In Progress | Medium | Medium | Candidate | Partial | Conditional | Conditional Go | Rejected | Acceptable | PUT | 204 | Anon Key | Sprint 26 | 1.0.1 | Config/Env | Live Practice Coach | Candidate App | Pro User | Rohan Mehta | Live Coach | Stub | Partial | Completed
Blocked | Not Run | Low | Low | CI | Safari | Android Phone | Linux | N/A | Failed | Fixed | Low | Low | Partial | Not Tested | Blocked |  | Deferred | Poor | PATCH | 400 | Service Role | Sprint 27 | 1.1.0 | Race Condition | Mock Interview | Admin Portal | Max User | Priya Nair | Sessions | Dead Code | N/A | Blocked
Deferred | N/A |  |  | Electron Dev | Electron | iPad | iOS |  | Blocked | Retest |  |  |  | N/A |  |  |  | Critical | DELETE | 401 | Webhook HMAC | Hotfix |  | UI Regression | Sessions & Debriefs | Electron Overlay | Admin | Dev Patel | Analytics | Not Built |  | Deprecated
Ready | In Progress |  |  | Electron Packaged | N/A | Android Tablet | Android |  | Deferred | Closed | [8 empty] | OPTIONS | 402 | API Key Header |  |  | API Contract | Analytics & Usage | All Portals |  |  | Prep
Complete | [9 empty] | Won't Fix | [9 empty] | 403 |  |  |  | DB/RLS | Prep Lab |  |  |  | Docs
Active | [9 empty] | Duplicate | [9 empty] | 404 |  |  |  | Third-party | Documents & Resumes |  |  |  | Scheduling
[20 empty] | 409 |  |  |  | Design Gap | Answer Bank |  |  |  | Growth
[20 empty] | 429 |  |  |  | Unknown | Interviews & Calendar |  |  |  | GovExams
[20 empty] | 500 |  |  |  |  | Company Research |  |  |  | Platform
[20 empty] | 501 |  |  |  |  | Notifications & Profile |  |  |  | Admin
[25 empty] | Referrals & Guide |  |  |  | Billing
[25 empty] | Gov Exam Mock Tests |  |  |  | Desktop
[25 empty] | Settings |  |  |  | QA Lead
[25 empty] | Admin Portal |  |  |  | Dev Lead
Marketing Site
Billing & Credits
Electron Desktop Overlay
Security & Platform